## Sheet1
Sprint 4 Burndown chart
Task | Estimate time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Story 10: Package Delivery Notifications | 6.5
T1 Add an email notification system for notifying users when their delivery is completed | 5 | 5 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2 Write Test cases | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3 Verify story is complete (acceptance test) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 19: Delivery Delay notifications | 6.5
T4 Add an email notification system for alerting users to delays in the delivery of their package | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
T5 Write test cases | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
T6 Verify story is complete | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Story 20: Update Delivery Request Form | 5
T7 Create a form on the website that can update existing database entries for users to modify their order information | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
T8 Write test cases | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
T9 Verify story is complete(acceptance test) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Story 06: View daily deliveries | 5
T10 Edit the website to allow looking up of all entries in package delivery with a date filter | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
T11 Write Test cases | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
T12 Verify story is complete (acceptance test) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Story 12: Package Delivery Cost Estimator | 6 | [15 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
T13 Create a cost per weight table | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Story Point Left: | 15 | 15 | 14 | 13 | 12 | 11 | 10 | 7 | 6 | 5 | 3 | 1 | 1 | 0
T14 Link the weight given in the form to call a given cost | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Spend Hour Per Day | 0 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1 | 3 | 3.5 | 3 | 2 | 2 | 1
T15 Write test cases | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Total hour Left: | 29 | 28 | 27 | 26 | 25 | 23 | 21.5 | 20.5 | 17.5 | 14 | 11 | 8 | 4 | 0
T16 Verify story is complete(acceptance test) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Velocity is stories per day